## Slide 1
Project Conception and Initiation
Project Definition and Planning
Project Execution and Control
Project Close

## Slide 2: Initiate the Project
Develop a plan to conduct a successful project
Create a project schedule
Plan your communication
Identify assumptions and risks
Determine quality plan
Plan for go live

## Slide 3: Create a Project Schedule

## Slide 4: Project Schedule Basics
What?
A timetable for a project
Lists project’s milestones, activities, and deliverables
Shows assigned resources that will perform the work
Why?
Gives realistic expectation for completion of the project
Reduces the chance for cost overruns
Shows task assignments

## Slide 5: Steps to Create a Project Schedule
Understand project deliverables
Define activities and organize into sequence
Define milestones
Assign available resources to activities
Determine and document activity durations
Outline resource availability and constraints
Set and analyze schedule

## Slide 6: Project Schedule Example
Replacing a door knob

## Slide 7: #1) Understand project deliverables
Projects have one to many deliverables that need to be met in order for the project to be deemed complete and successful.
Deliverables:
  1.0 - Door knob

## Slide 8: #2) Define activities and organize sequence
Activities show what needs to be completed in order to achieve the deliverables.
Activities:
  1.1 – Determine door knob needs
  1.2 – Conduct research
  1.3 – Purchase door knob
  1.4 – Remove old door knob
  1.5 – Install new door knob
  1.6 – Validate installation

## Slide 9: #3) Define milestones
Milestones are achievements of the project. Used to understand how the project is advancing.
Activities:
  1.1 – Determine door knob needs
  1.2 – Conduct research
  1.3 – Purchase door knob
  1.4 – Remove old door knob
  1.5 – Install new door knob
  1.6 – Validate installation
Milestones:
  Project Kickoff
  Needs Identified
  Installation
  Project Close

## Slide 10: #4) Assign available resources to activities
Resources need to be allocated to complete the activities
Activities:
  1.1 – Determine door knob needs 
  1.2 – Conduct research 
  1.3 – Purchase door knob 
  1.4 – Remove old door knob 
  1.5 – Install new door knob 
  1.6 – Validate installation 
Resource:
  Jeremy, Beth
  Jeremy
  Beth
  Jeremy
  Jeremy
  Jeremy, Beth, Megan

## Slide 11: #5) Determine activity durations
Each activity will take time to complete
Activities:
  1.1 – Determine door knob needs 
  1.2 – Conduct research 
  1.3 – Purchase door knob 
  1.4 – Remove old door knob 
  1.5 – Install new door knob 
  1.6 – Validate installation 
Resource:
  Jeremy, Beth
  Jeremy
  Beth
  Jeremy
  Jeremy
  Jeremy, Beth, Megan
Duration (hrs):
  4 (2 each)
  6
  3
  2
  1
  3 (1 each)

## Slide 12: #6) Outline resource availability/constraints
Resources are tied up in other projects and have days in which they are unavailable for activities. It is important to take that into account when you create a schedule.
Jeremy
Availability: M-F 6pm-11pm
Constraints:
  No availability Sa-Su
  7/4
  9/16 – 9/26
Beth
Availability: M-F 1pm-5pm, 8pm-10pm
Constraints:
  No availability Sa-Su
  7/4
Megan
Availability: M-F 6pm-9pm
      Sa-Su 10am-4pm
Constraints:
  6/27 - 7/4
  7/11

## Slide 13: #7) Set and analyze schedule
Activity | Duration | Start | End | Resource | Notes
Project Kickoff | 0.5 | 7/1 | 7/1 | All | 
Determine door knob needs (4) | 2 | 7/2 | 7/2 | Jeremy | Discussion needs to be in tandem
 | 2 | 7/2 | 7/2 | Beth | 
Conduct research | 6 | 7/3 | 7/4 | Jeremy | 
Purchase door knob | 3 | 7/5 | 7/5 | Beth | 
Remove old door knob | 2 | 7/6 | 7/6 | Jeremy | 
Install new door knob | 1 | 7/6 | 7/6 | Jeremy | 
Validate installation (3) | 1 | 7/7 | 7/7 | Jeremy | 
 | 1 | 7/7 | 7/7 | Beth | 
 | 1 | 7/7 | 7/7 | Megan | 
Project Close | 0.5 | 7/8 | 7/8 | All | 

## Slide 14
Activity | Duration | Start | End | Resource | Notes
Project Kickoff | 0.5 |  |  | All | 
Determine door knob needs (4) | 2 |  |  | Jeremy | Discussion needs to be in tandem
 | 2 |  |  | Beth | 
Conduct research | 6 |  |  | Jeremy | 
Purchase door knob | 3 |  |  | Beth | 
Remove old door knob | 2 |  |  | Jeremy | 
Install new door knob | 1 |  |  | Jeremy | 
Validate installation (3) | 1 |  |  | Jeremy | 
 | 1 |  |  | Beth | 
 | 1 |  |  | Megan | 
Project Close | 0.5 |  |  | All | 
7/1
7/1
7/11
7/5
7/1
7/5
7/5
7/8
7/8
7/11
7/1
7/11
7/11
7/15
7/7
7/15
7/8
7/8
7/11
7/12
7/12
7/12

## Slide 15: Project Schedule Activity
Create a Project Schedule template
Things to keep in mind:
Schedule should be intuitive to read and understand
Clearly define activities and owners
Include a section to document constraints utilized to assign activities and dates

## Slide 16: Plan Your Communication

## Slide 17: Plan Your Communication
Defines the general communication requirements for your project
Increases knowledge about the project and why it is important
Helps to gain acceptance of the project among employees and stakeholders
Provides an opportunity for feedback from stakeholder group

## Slide 18: Plan Your Communication
Kickoff Meeting
Project Status Reports
Meeting Notes

## Slide 19: Plan Your Communication
Define the key objective, topic of discussion, delivery method, frequency, audience, and role that owns responsibility for making it happen.

## Slide 20: Communication Plan Format
While the details may be slightly different for each project, here is my standard for these three communication items.

## Slide 21: Communication Plan Activity
Create a Communication Plan Template
Things to keep in mind:
Keep it simple – overcomplicated plans do not get read
Contain at least the three communications types mentioned
Think through various scenarios that could occur and validate you know how you would communicate that to the project team

## Slide 22: Identify Assumptions & Risks

## Slide 23: What is an assumption?
Circumstances or events that are expected to occur during the project life-cycle.

## Slide 24: Identifying assumptions
All team members have assumptions. The key is to identify the assumptions of the various members, including yourself.
Conduct project plan walk-throughs Review activities and order of execution Discuss what activities entail
Question everything Do I know this for a fact or am I making an assumption? If I believe this is a fact, what was the source of the info?

## Slide 25: Assumption examples
Team members will be made available for the project
Business approval of the requirements will take two weeks
Project will have at least one dedicated Quality Assurance tester
Future end users will be available for onsite training

## Slide 26: Assumptions – Now you know, but what’s next?
Document and call out each assumption in status reports and meetings
Determine worst case if the assumption is incorrect
If determined costly, validate the assumption
If not possible to validate, treat the assumption as a risk

## Slide 27: What is a risk?
An uncertain event or condition that, if it occurs, has an effect on at least one project objective.
Such as:
  Scope
  Schedule
  Budget
  Quality
  User Adoption
  …

## Slide 28: Identifying risks
Starts at the beginning of the project and lasts through the closing
Schedule:
Not realistic
One activity delay will cascade
Unfamiliar areas could cause inaccurate estimates
Requirements:
Poorly defined
Limited user feedback in determining
Customer:
Insists on new requirements
Executive sponsor not engaged
Design too complex for users
Limited business testing resources
Notes: The earlier it is identified the better

## Slide 29: Risks – Now you know, but what’s next?
Document and call out each risk in status reports and meetings
Determine ways to eliminate the risk or reduce the effect if it comes true
Schedule:
Not realistic
One activity delay will cascade
Unfamiliar areas could cause inaccurate estimates
Requirements:
Poorly defined
Limited user feedback in determining
Customer:
Insists on new requirements
Executive sponsor not engaged
Design too complex for users
Limited business testing resources

## Slide 30: Assumptions and Risks Final Thought
Don’t be complacent as risks and assumptions can completely derail a project.
  Identify
  Validate
  Communicate
  Take Action

## Slide 31: Determine Quality Plan

## Slide 32: Quality Plan
Addresses the quality requirements, standards, and quality assurance mechanisms for a project
Sections:
  Testing and Quality Assurance
  Defect Management
  Training Requirements

## Slide 33: Testing and Quality Assurance
Most important section of the Quality Plan
Define who is responsible for testing
Identify quality objectives for the project
Determine quality approach

## Slide 34: Defect Management
Defects and bugs will be discovered during testing
Guidelines for what is considered a defect/bug
Details on where to document
Instructions on how to manage the defects

## Slide 35: Training Requirements
Defines training for the project team at the onset of the project and the training needed for users at the go live
Identify project team skill gaps to understand training needs
Understand staff training needs to utilize final product
Define steps to get staff trained

## Slide 36: Quality Plan Activity
Create a Quality Plan Template
Things to keep in mind:
Keep it simple – overcomplicated plans do not get read
Should at least contain the sections mentioned in the lectures
Always ask yourself, “what problem is this solving?”

## Slide 37: Plan for Go Live

## Slide 38: Go Live
Plan how…
The system will be rolled out to users
The users will be supported at go live
The system will be turned over to support

## Slide 39: System Rollout to Users
All at once
  All users utilize the full system on day 1
Phased
  All users utilize pieces of the system in staggered phases
Pilot
  A subset of users use the full system on day 1
  Other users use the full system at a future date

## Slide 40: User Support at Go Live
Identify resources available to support the go live
Document for users to reference for go live support
  Instructions for defect tracking
  Who to contact if issue halts work
Schedule reoccurring meeting with subset of users to discuss issues

## Slide 41: System to Support
Procedure manual
Documentation of the design
Instructions to troubleshoot common issues
Escalation contact information

## Slide 42: Go Live Plan Activity
Create a Go Live Plan Template
Things to keep in mind:
Keep it simple – overcomplicated plans do not get read
Should at least contain the sections mentioned in the lectures
Format and visual appeal are not important – stick to the facts