## Slide 1
Project Conception and Initiation
Project Definition and Planning
Project Execution and Control
Project Close

## Slide 2: Initiate the Project
Deliverables are developed and completed while the project progression is closely monitored
Kick off the project and reveal project plans
Monitor and mitigate risk
Conduct status meetings
Utilize a change management process

## Slide 3: Project Kickoff

## Slide 4: Project Kickoff: What
First meeting with the full project team
Introduces everyone to other members of the project team
Details the objective of the project
Outlines plans to be successful
If you do your job right, the team should leave energized and excited to get started!

## Slide 5: Project Kickoff: Setup
Schedule at the beginning of the project
Generally lasts one hour
Include the full project team
Prior to the meeting, create and distribute an agenda
Send all project planning documents ahead of time
Ask team member to review project details before the meeting

## Slide 6: 7 Steps to a Successful Project Kickoff
Introduce yourself – be relaxed and personable
Complete brief introductions of the project team
Define the project, its purpose, its goals, and the deliverables
Go over project schedule – discuss each activity
Discuss defined risks and assumptions – add to your list as appropriate
Review the communication plan – set frequency, schedule, attendees, and expectations on status meetings
Ask for feedback

## Slide 7: Project Kickoff Activity
Create a Project Kickoff PowerPoint deck
Keep it high level so it can be utilized for many projects
Could be one slide per agenda item
Could otherwise be one slide with full agenda on it
Will be used as a guide for the meeting

## Slide 8: Monitor and Mitigate Risks

## Slide 9: Monitor and Mitigate Risks
Ignored risks cause failed projects.
Continually identify, evaluate, communicate, and mitigate identified risks.

## Slide 10: Conduct Status Meetings

## Slide 11: Status Meetings
Status meetings are used to update the team on the progress of the project, collaborate on the status of activities, and set expectations for progress to continue forward.

## Slide 12: Status Meetings: Agenda
Static Agenda:
Roll call
Discuss new risks or issues
Detailed review of the project and status of activities
Define critical activities
Collaborative question and answer
Summary of takeaways from the meeting
Conclude
Send meeting notes and takeaways with assigned owners

## Slide 13: Status Meetings: Best Practices
Start meetings on time
Fully understand the project status and risks
Keep the team accountable
Don’t exceed one hour in length
Discuss and remove major roadblocks
Conduct breakoff meetings to discuss issues that don’t involve the full team
Be cognizant of the time commitments and keep the meeting to the project critical items

## Slide 14: Status Meetings Activity
Create a static Status Meeting Agenda Document
Utilize the teachings of the previous lectures to ensure you have the necessary agenda items.
(optional) Add a description near each item to give more details as to what is covered.

## Slide 15: Change Management Process

## Slide 16: Change Management Process
Allows for projects to remain flexible to ever changing business needs while also understanding the impact of the requested change.
Identify the need for change
Define the reason for change, priority, and project impact in a Change Request document
Present to Project Sponsor for potential approval
If approved, execute the change
If not approved, inform the project team and make determination if this should be considered in a future phase

## Slide 17: Making Adjustments

## Slide 18: Making Adjustments
As the project unfolds, there will be changes
Remain flexible
Hold people accountable
Build and maintain relationships
Drive towards project success