## Slide 1
Project Conception and Initiation
Project Definition and Planning
Project Execution and Control
Project Close

## Slide 2: Initiate the Project
Officially close out the project and understand lessons learned
Confirm project completion and verify business requirements are met
Conduct project (post mortem) review
Transition to support/operations

## Slide 3: Project Completion

## Slide 4: Project Completion Verification
Validates project objectives have been met and analyzes if the project adhered to budget, schedule, and quality requirements.
Completed by the Project Manager
Format and level of detail varies per project
States any open issues or risks
Outlines high level customer satisfaction on project

## Slide 5: Project Completion Activity
Create a Project Completion Template
The document should…
Give brief summary of project
List project objectives and give analysis if they were met
Detail any open risks or issues
Describe level of customer satisfaction with the end result

## Slide 6: Conduct Project Review

## Slide 7: Project Review
Brings the project team and other stakeholders together to discuss both what went well with the project and what didn’t go as well.
Can be split into multiple meetings if very large project
Send a survey ahead of time to collect feedback
Prepare and send an agenda prior to the meeting

## Slide 8: Feedback Survey
A feedback survey should be sent at least one week before the meeting asking about thoughts on various aspects of the project.
Overall, how successful do you think this project was? What went right (list up to 3 things)?
What obstacles did you face (list up to 3 things)?
What needs improvement/should have been done differently (list up to 3 things)?
Do you have any other comments?

## Slide 9: Review Meeting
Tend to focus on the negative, so keep it non-confrontational and be sure to ask about what went right
Work through each section of the feedback survey and facilitate positive and meaningful discussion
Take notes both on positive and constructive feedback

## Slide 10: Post Review Meeting
Analyze the results from the review meeting and recommend process or procedural changes that should be made for future projects.
“Those who do not learn from history are doomed to repeat it”
                - George Santavana

## Slide 11: Execute Transition

## Slide 12: Product Transition
Projects that have a deliverable such as a system or a product need to have someone responsible for its long term future.

## Slide 13: Steps to Transition
Bundle up all necessary project documentation and make it accessible to the support team
Schedule the training for the support team
Review common questions and issues
Execute transition

## Slide 14: Flex Your New Muscles

## Slide 15: Full Project Activity
Now it is YOUR turn!
Think of a project you need to complete at home or work
Utilize your created templates and work through each step of the four Project Management stages
  Project Conception and Initiation
  Project Definition and Planning
  Project Execution and Control
  Project Close
Adjust and tweak your templates as appropriate
Reflect on your management of the project